## Sheet1
| AVD Testing Checklist | Ready for Test |  |  | Test Result (Lab3) | Test Result (Client Name) | Defect ID | Modifications or updates requested (where required)
| Scenario being tested: | Internal Test | Pilot Wave 1 | Pilot Wave 2 | Current Result Status: | Client Verified Result Status: | Defect ID#: | Notes:
1 | AVD Access: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
1.1 | Verify that device is accessable using web portal
1.2 | Verify that Device is registered to Entra ID and Intune enrolled
1.3 | Verify access over VPN connections (if required)
1.4 | Verify Proxy configuration (if required)
2 | Peripherals: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
2.1 | Check bluetooth peripherial redirection is configured as per design
2.2 | Check headset and microphone redirection is configured as per design
2.3 | Check USB device redirection onfigured as per design
2.4 | Check redirected webcam and microphone are detected by Teams
2.5 | Check functionality of any devices connected by propriaty docking stations are being redirected
3 | License activation: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
3.1 | Verify the Windows license is enterprise and activated.
3.2 | Verify the Microsoft Office applications are licensed and activated.
4 | Image customisation: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
4.1 | Verify Intune is customising marketplace image with settings defined in Intune
4.2 | Verify the applications available in Company Portal is deploying successfully
4.3 | Verify standard applications for environment as defined in the design are deployed to hosts
5 | Application environment: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
5.1 | Ensure Windows Defender Application Control is configured and functional (if required)
5.2 | Check the functionality of all default applications deployed to the AVD environment.
5.3 | Verify functionality of applications when accessing them from various device types.
5.4 | Check Edge browser first boot experience.
5.5 | Check Edge browser policy is configured as designed
5.6 | Check Edge browser plugins ar deployed and functional (where applicable)
6 | User groups and policies: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
6.1 | Validate user authentication and auth process (controlled by group membership/access packages)
6.2 | Test all user groups/access packages and verify access to correct host pools.
6.3 | Check security policy is applying correctly for all user groups/access packages.
7 | Company Portal base functionality: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
7.1 | Confirm the Company Portal application is accessable in dedicated host pools
7.2 | Ensure packaged applications are deploying when requested via the company portal.
7.3 | Validate real time status toast popups are visible during installation process.
8 | Default user applications: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
8.1 | Verify list of applications is matching with the design and functional.
8.2 | Test customisation and latency when performing required application functions.
9 | Uninstallation/redeployment of Company Portal deployed applications: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
9.1 | Test the uninstallation function from within company portal for a custom deployed application
9.2 | Validate the redeployment of a failed custom applicaion deployment via Company Portal
10 | Compatibility and performance: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
10.1 | Test application compatibility in all host pools.
10.2 | Check the performance imapact of installed applications on system resources when running under typical load.
11 | Security integration: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
11.1 | Verify Windows firewall settings (if required).
11.2 | Validate the securirty policy settings are not confliting with application functionality.
11.3 | Test the integration of WDAC with deployed applications (where WDAC is configured).
12 | Network and connectivity: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
12.1 | Verify network connectivity to on premises resources (where required).
12.2 | Verify network connectivity to Azure and other cloud hosted resources (where required).
13 | User experience: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
13.1 | Confirm user notifiactions are being received or surpressed based on configuration defined in design.
13.2 | Confirm FSLogix profile portability is functional and performant in multisession host pools.
14 | M365 application functionality: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
14.1 | Test creating, editing, saving and sharing of a Microsoft Word file.
14.2 | Test creating, editing, saving and sharing of a Microsoft Excel file.
14.3 | Test creating, editing, saving and sharing of a Microsoft Powerpoint file.
14.4 | Test creating, editing, saving and sharing of a Microsoft Publisher file (if applicable).
14.5 | Test creating, editing, saving and sharing of a Microsoft OneNote notebook (if applicable).
14.6 | Test functionality of Microsoft Teams (calls, chat, video, audio, teams management etc.).
14.7 | Test automatic sign-in,creating, editing, saving and sharing of files using Microsoft OneDrive.
14.8 | Test creaing, editing, saving, sending, receiving, attaching and labeling (if applicable) is functional in Microsoft Outlook.
14.9 | Test Microsoft Remote Desktop connecton application is functional and can access relevant network endponts.
15 | M365 Migrated Content | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
15.1 | Test any relevant migrated content is accessable to AVD hosts (applicable for migration scenarios only).
16 | Specialised client requested tests: | YES or NO | YES or NO | YES or NO | PASS or FAIL | PASS or FAIL | ID#:
16.1 | Example 1
16.2 | Example 2
16.3 | Example 3